SOFTWARE ENGINEERING & WEB DEVELOPMENT LAB MANUAL

PROJECT CASE STUDY: LEDGERLY — INVOICE & QUOTATION GENERATOR PWA

# Experiment No. 12: Cost Estimation Using the Basic COCOMO Model

## 1. Pre-Requisites

• Understanding of software cost estimation models (Barry Boehm's Basic Constructive Cost Model - COCOMO).
• Knowledge of project complexity categories: Organic (small team, familiar domain), Semi-Detached, and Embedded.
• Familiarity with mathematical formulas for Effort (Person-Months), Development Schedule (Months), Staffing, and Budgeting.

## 2. Objective

To perform a realistic cost, effort, and duration estimation for the Ledgerly Invoice Generator based on effective Lines of Code (LOC) using the Basic COCOMO Organic model tailored to a student/academic software engineering project.

## 3. Software Sizing (Effective LOC Count)

For cost estimation, only core application source code (excluding boilerplate comments, blank lines, and external vendor bundles) is considered:

| Module / Component | Technology Stack | Effective Lines of Code (LOC) |
| --- | --- | --- |
| Application Structure & View Templates | HTML5 | 250 LOC |
| Design System, Layouts & Print Styling | CSS3 | 750 LOC |
| Core Calculation, Router & Invoice Logic | Vanilla JavaScript (ES6) | 1,350 LOC |
| Offline Cache & Service Worker | JavaScript PWA | 50 LOC |
| Validation & Verification Test Logic | Python / JS | 100 LOC |
| Total Effective Project Sizing | Web Technologies | 2,500 LOC (2.5 KLOC) |

Total Software Size (KLOC): 2.5 KLOC.

## 4. Project Classification & COCOMO Formulas

Project Classification: Organic Model
Justification: Ledgerly is developed by a small, focused team (1–2 student developers) working in a familiar, well-understood web technology environment (HTML5, CSS3, JavaScript) with flexible requirements and no rigid hardware constraints.

Organic Model Coefficients:
• a = 2.4, b = 1.05
• c = 2.5, d = 0.38

Formulas:
• Effort (E) = a × (KLOC)^b [Person-Months]
• Development Time (D) = c × (E)^d [Months]
• Average Staffing = E / D [Developers]
• Total Cost = Effort × Cost per Person-Month

## 5. Mathematical Step-by-Step Calculation

Step 1: Calculate Development Effort (E)
E = 2.4 × (KLOC)^1.05
E = 2.4 × (2.5)^1.05
Calculate exponent: 2.5^1.05 ≈ 2.616
Thus, Effort (E) = 2.4 × 2.616 = 6.28 Person-Months (PM)

Step 2: Calculate Development Time / Duration (D)
D = 2.5 × (E)^0.38
Calculate exponent: 6.28^0.38 ≈ 2.012
Thus, Duration (D) = 2.5 × 2.012 = 5.03 Months (~5 Months / 1 Academic Semester)

Step 3: Calculate Average Staffing
Staff = Effort / Time
Staff = 6.28 / 5.03 ≈ 1.25 (~1 to 2 Developers)
This precisely matches the student team size for an academic mini-project.

Step 4: Realistic Cost Estimation
• Student Project (Actual College Execution): ₹0 (Zero development cost)
• Academic / Intern Stipend Benchmark (@ ₹15,000/PM):
  Total Cost = 6.28 PM × ₹15,000 = ₹94,200 (~₹0.94 Lakhs)
• Junior Developer Benchmark (@ ₹20,000/PM):
  Total Cost = 6.28 PM × ₹20,000 = ₹1,25,600 (~₹1.25 Lakhs)

## 6. COCOMO Estimation Summary Table

| Estimation Parameter | Calculated Value | Remarks |
| --- | --- | --- |
| Effective Code Size | 2,500 LOC (2.5 KLOC) | Core source code |
| COCOMO Category | Organic | Small team, familiar web stack |
| Estimated Effort (E) | 6.28 Person-Months | Effort required |
| Development Time (D) | 5.03 Months (~20 Weeks) | Aligns with 1 semester timeline |
| Recommended Team Size | 1 – 2 Developers | Matches student project allocation |
| Actual Student Cost | ₹0 | Zero-cost college coursework |
| Nominal Academic Cost | ₹94,200 (~₹0.94 Lakhs) | Estimated at student stipend rate |

## 7. Conclusion

Experiment 12 provided a realistic, grounded estimation for Ledgerly using the Basic COCOMO Organic model. Sizing the core system at 2.5 KLOC resulted in 6.28 person-months of effort, a 5-month development timeline (matching an academic semester), and a team of 1–2 developers, confirming the project's practical feasibility.